## Slide 1
WEEK 3 · SESSION 1
Technology Assessment / Risk Management / Trade Study
Session 1: Readiness, risk and the measures that track it
Today: technology readiness, the risk register, technical performance measures
Session 2: the trade study, worked in full, and the Lab L3 launch
Your Team Record grows: readiness assessment, risk register, TPMs, trade study

## Slide 2
Figure. Waits are forecast to grow as Year-2 demand reaches 240 trips/day. The board proposes six more aircraft. (FICTIONAL)
The driving question: should AeroLink buy six more aircraft?
SCENARIO (FICTIONAL)
Demand will reach 240 trips/day. The board proposes 6 more aircraft: 18 in all.
A · Yes: more aircraft, shorter waits
B · Only with more charging
C · Build a seventh vertiport instead
D · Cannot tell yet

## Slide 3
Figure. Technical assessment, risk management and decision management overlap; what they share is uncertainty. One AeroLink artifact in each.
Sources: R17 p.481; R17 p.485; R39s p.1668
Three processes, one subject: uncertainty
Risk: the effect of uncertainty on objectives, or probability and severity of harm
Uncertainty: not having accurate or sufficient knowledge
Measurement gives indicators for risk analysis
Decision management evaluates alternatives that treat risks

## Slide 4
Figure. Risks and opportunities sit strictly between probability 0 and 1; an issue sits at exactly 1. Assumptions and unknowns are about knowledge.
Sources: R39q p.1610; R39r p.1582; R46 p.127; R13 p.565
Five kinds of entry: assumption, risk, opportunity, unknown, issue
Risk: 0 < probability < 1, consequence > 0, in the future
Issue: has occurred or is certain (probability 1)
Opportunity: an outcome better than expected
Assumption: taken as true; must be validated
Unknown: information not yet available (TBD/TBR)

## Slide 5
Figure. The nine technology readiness levels as a staircase, grouped by the environment in which the technology has been shown to work.
Sources: R16 p.766; R44 p.112
What a readiness assessment is for
Qualifies technology development and supports investment decisions
A TRL summarizes a technology’s degree of maturity
Nine levels: basic principles (1) to proven in mission operations (9)
Assess maturity and risk of the critical technologies

## Slide 6
Figure. TRL measures demonstrated maturity in an environment. Producibility, integration and changed environments need other questions.
Sources: R16 p.767; R16 p.768
The scale, read exactly, and what it does not tell you
TRL | SEBoK wording
4 | Component validation in laboratory environment
5 | Component validation in relevant environment
6 | Prototype demonstration in a relevant environment
7 | Prototype demonstration in an operational environment
Not measured: producibility, integration, criticality, changed environments

## Slide 7
Figure. Technology matures along an s-curve; TRL is the accepted way to measure its rising slope. Hype often runs ahead of maturity.
Sources: R60 p.524; R60 p.525
Maturity in practice: hype, the s-curve and shared meanings
Hype can draw funding to unsuitable technology: assess before committing
TRL measures the rising slope of the s-curve
Agree what “relevant environment” means for your system
TRL does not say how well a technology fits your architecture

## Slide 8
Figure. Two acceptable TRL claims and one that is not: cite the evidence, or record the claim as an assumption with an owner and a validation action.
Sources: R60 p.525
Evidence, or a labeled assumption
COURSE RULE
Every TRL cites evidence, or is recorded as an assumption with an owner and a validation action.
Most student TRLs will be assumptions: acceptable when labeled
Interpret the environment words for your system

## Slide 9
Figure. AeroLink’s readiness assessment. The lowest TRL among the critical technologies leads the summary. Every TRL rests on an assumption. (FICTIONAL)
Sources: R16 p.767; R60 p.525; R60 p.526
Worked example I: AeroLink’s three enabling technologies
Select: the critical technologies the requirements depend on
Rate: each on the scale, with evidence or a labeled assumption
Judge: criticality and what the TRL does not tell
Summarize: the lowest critical TRL and its maturity risk

## Slide 10
Figure. The risk process as a loop: each activity answers one question and produces something the next one uses.
Sources: R17 p.482; R46 p.124; R46 p.125
The risk process: five activities and what each produces
Planning: what is our process, and our scales?
Identification: what can go wrong?
Analysis: how likely, how severe?
Mitigation: accept, avoid, transfer or control?
Monitoring: how has the risk changed?

## Slide 11
Figure. A risk in the condition–if–then form, with the most common defect struck out: a mitigation written into the statement.
Sources: R17 p.483; R46 p.125; R61a p.630; R61a p.631; R61a p.633
Writing a risk: condition, if, then
Condition: what is known today, the root cause
If: the uncertain risk event
Then: the consequences if it occurs
Never write the mitigation into the statement

## Slide 12
Figure. The 5 × 5 reporting matrix with AeroLink’s 11 risks plotted by likelihood and consequence. Cell levels as in DoD Figure 4-9. (FICTIONAL ratings)
Sources: R17 p.483; R46 p.125; R46 p.126; R61b p.635; R61b p.637
Rating risks: defined scales and the reporting matrix
Likelihood | Probability band
1 Not likely | > 1 % to ≤ 20 %
2 Low likelihood | > 20 % to ≤ 40 %
3 Likely | > 40 % to ≤ 60 %
4 Highly likely | > 60 % to ≤ 80 %
5 Near certainty | > 80 % to ≤ 99 %
Consequence: deviation from the performance, schedule or cost baseline, tailored to the program

## Slide 13
Figure. The product of two ordinal ratings ranks a safety risk below a performance risk, and gives the same number to cells the matrix treats differently.
Sources: R17 p.483; R17 p.486; R61b p.636; R61b p.637
What the matrix cannot say: ordinal scales are not numbers
Same product: 1 × 5 = 5 × 1 = 5, but the cells differ
Wrong order: fade 3 × 4 = 12 outranks runaway 2 × 5 = 10
Course rule: rank by cell level, then consequence
Cardinal: multiply only measured quantities

## Slide 14
Figure. Four handling options, each shown with one AeroLink risk. Transfer changes who pays, not what passengers experience.
Sources: R17 p.484; R17 p.485; R46 p.126; R61c p.642; R61c p.644
Handling options: evaluate all four before choosing
Avoid: change requirements or plans so the risk goes away
Control: reduce likelihood, consequence or both
Transfer: move accountability to a willing party
Accept: a deliberate, approved decision; then monitor
Evaluate all four; do not default to mitigation

## Slide 15
Figure. Adversity, whether attack, fault or outage, degrades capability. Resilience aims to avoid, withstand and recover; security limits loss of assets.
Sources: R24 p.1203; R24 p.1204; R24 p.1208; R25 p.1229; R25 p.1231; R39q p.1610
Security and resilience risks belong in the same register
Resilience: provide required capability when facing adversity
Objectives: avoid, withstand, recover
Security: freedom from conditions that lead to loss of assets
Adversity includes attacks, faults and outages
Plan risk management to take these risks

## Slide 16
Figure. Two register entries expanded: the condition–if–then parts, the ratings with reasons, the handling, and the requirements each threatens. (FICTIONAL)
Sources: R61a p.630; R17 p.484; R46 p.126; R24 p.1206; R25 p.1231
Worked example II: writing, rating and handling two risks
Write: condition, if, then; no treatment inside
Rate: likelihood and consequence, each with a reason
Handle: compare all four options; owner, treatment, trigger
Link: to the requirements and scenarios it threatens

## Slide 17
Figure. A burn-down for battery fade: planned and actual risk level over time, the trigger on its TPM, and the “sea of green” trap.
Sources: R17 p.484; R17 p.485; R17 p.486; R46 p.127
Monitoring, triggers and the pitfalls to avoid
Monitor with metrics, including TPMs, against a burn-down
Sea of green: track the risk, not the plan
Done only for reviews → keep the register continuous
Automatic mitigation → evaluate all four options
Band-aid treatment → address the root cause

## Slide 18
Figure. AeroLink’s register entries on the left, the Week 2 artifacts they affect on the right. Unknowns link to the TBDs of the requirements. (FICTIONAL)
Sources: R13 p.565; R17 p.483
Worked example III: the register, linked to the package
Every entry affects named requirements, capabilities or scenarios
Each Week 2 TBD or TBR links to an unknown
Issues kept in a separate log
Owners and triggers make the register actionable

## Slide 19
Figure. The measures hierarchy with the TPM level added: a TPM tracks, over development, a design parameter behind an MOP.
Sources: R15 p.532; R44 p.113; R44 p.116
From MOE and MOP to TPM
TPMs: measures collected over time to see trends and forecast progress to plan
Estimated early from models; replaced by demonstrated data
Leading indicators of deficiencies and risk
Good TPM: quantifiable, routine, planned profile, tied to a risk

## Slide 20
Figure. For a lower-is-better TPM: the current best estimate, plus contingency to the worst case, then margin up to the threshold. The objective lies below.
Sources: R44 p.117
Current estimate, contingency, worst case and margin
WCE = CBE + contingency margin = threshold − WCE
CBE = current best estimate contingency = allowance for uncertainty; shrinks as the design matures margin = growth still possible within the threshold
NOTE
Higher-is-better: subtract contingency, and margin = WCE − threshold.

## Slide 21
Figure. Landing energy reserve: planned worst case at five reviews against the 20 % threshold, and a hypothetical month-6 reading that crosses the trigger. (FICTIONAL)
Sources: R44 p.116; R44 p.117
Worked example IV: AeroLink’s TPMs, margins and planned profile
TPM | CBE | Cont. | WCE | Margin
Charge time to dispatch threshold (min) | 18 | 1.0 | 19 | 1.0
Pad-edge noise (dBA) | 63.5 | 1.0 | 64.5 | 0.5
Landing energy reserve on the design trip (%) | 23 | 1.5 | 21.5 | 1.5
Compute: worst case and margin
Read: the planned profile

## Slide 22
Figure. Battery cells (TRL 5) → capacity fade risk → landing-energy TPM → planned landing reserve → assurance of flight within safety limits. A test result propagates along the chain. (FICTIONAL)
Sources: R44 p.113; R17 p.484
One chain through all three instruments
Technology → risk → TPM → requirement → need
12 % fade: reserve 21.25 %, margin 0.25: trigger fires
15 % fade: reserve 18.5 %, below the threshold
One result changes the whole chain

## Slide 23
Figure. A trade study frame with two sockets highlighted: maturity and risk enter as criteria, as must-meet screens, or as conditions on the decision.
Sources: R18 p.464; R24 p.1208
What Session 2 needs from today
Identify uncertainty and assess risk for each decision
Maturity and risk enter as criteria, screens or conditions
Resilience can be a criterion; security a must-meet screen
Bring your enterprise’s technologies and one decision

## Slide 24
Exit: retrieval and preparation
ONE-MINUTE PAPER
Rewrite as condition–if–then: “The new app might be late.”
Each member: two technologies your enterprise depends on, a first TRL and its basis
One decision your team will soon face
Read the trade-study pages listed on the week page

## Slide 25
References and credits
R13 · SEBoK v2.14 (2026), “System Requirements Definition”, p.565
R15 · SEBoK v2.14 (2026), “Measurement”, p.532
R16 · SEBoK v2.14 (2026), “Product Systems Engineering Special Activities”, p.766–768
R17 · SEBoK v2.14 (2026), “Risk Management”, p.481–486
R18 · SEBoK v2.14 (2026), “Decision Management”, p.463–474
R24 · SEBoK v2.14 (2026), “System Resilience”, p.1203–1204, 1206, 1208–1209
R25 · SEBoK v2.14 (2026), “System Security”, p.1229, 1231–1232
R39q · SEBoK v2.14 (2026), “Risk (glossary)”, p.1610
R39r · SEBoK v2.14 (2026), “Opportunity (glossary)”, p.1582
R39s · SEBoK v2.14 (2026), “Uncertainty (glossary)”, p.1668
R44 · OUSD(R&E) Systems Engineering Guidebook (2021/2022), “Technical Assessment Process”, p.112–114, 116–117
R46 · OUSD(R&E) Systems Engineering Guidebook (2021/2022), “Risk Management Process”, p.124–127
R60 · The MITRE Systems Engineering Guide (2014), “Assessing Technical Maturity”, p.524–526
R61a · The MITRE Systems Engineering Guide (2014), “Risk Identification”, p.630–631, 633
R61b · The MITRE Systems Engineering Guide (2014), “Risk Impact Assessment and Prioritization”, p.635–637
R61c · The MITRE Systems Engineering Guide (2014), “Risk Mitigation Planning, Implementation, and Progress Monitoring”, p.642, 644
CREDITS AND LICENSES
SEBoK v2.14: “This material is used under a Creative Commons Attribution-NonCommercial ShareAlike 3.0 Unported License from The Trustees of the Stevens Institute of Technology.” (SEBoK, “Bkcase Wiki:Copyright”, PDF p.31). Quotations are short and cited; no SEBoK figure or table is reproduced.
OUSD(R&E) Systems Engineering Guidebook: Distribution Statement A. Approved for public release. Distribution is unlimited.
The MITRE Systems Engineering Guide: © 2014 by The MITRE Corporation. All rights reserved. Approved for public release; distribution unlimited (Case Numbers 10-4072 and 12-1089). Quoted briefly with attribution.
Figures are original drawings for this course; none redraws a figure from the sources.
AeroLink Urban Mobility is a fictional teaching case: every number, name and statement about it is a teaching value.